## Sheet1
Standard Name	Current Name	Usage	Status		Comments	Assigned Artist	Signing Artist		Statuses
show-menu	showmenu	showMenuBar action	final	3		Pinheiro	Vignoni		blank: not in theme	29	20,0%
view-fullscreen	window_fullscreen	full screen action	final	3	need 22 and 16 special version	Pinheiro	Vignoni		in theme	115	79,3%
view-restore	window_nofullscreen	de-full screen action	final	3	need 22 and 16 special version	Pinheiro	Vignoni
color-picker	colorpicker	color dialog button	final	3	think it can be set as final	Pinheiro	Vignoni		draft: pre-approval	25	17,2%
go-up	up	toolbar editor, action selector dialog, kate, kprinter	approval	2					approval: needs approval	18	12,4%
go-down	down	toolbar editor, action selector dialog, kate, kprinter	approval	2					final	72	49,7%
go-previous	back	back action, toolbar editor, action selector, kde print	approval	2
go-next	forward	forward action, toolbar editor, action selector, kdeprint	approval	2					Standard names	54
	example	overlay, none by default		Err:508	were can i find info about this ones	Pinheiro			Total icons	145
	screenshot	screenshot overlay, none by default		Err:508	were can i find info about this ones	Pinheiro
emblem-symbolic-link	link	link overlay	final	3		Vignoni	Vignoni
	zip	zip overlay	draft	1		Wimer
shared-file	share	share overlay		Err:508		Vignoni
edit-undo	undo	undo/redo action, text edit context menus, redo stack	final	3		Vignoni
edit-redo	redo	undo/redo action, text edit ctx menus, redo stack, print job mgr	final	3		Vignoni
edit-cut	editcut	text edit context menus	final	3		Pinheiro	Vignoni
edit-copy	editcopy	text edit context menus, kate, kdeprint	final	3		Vignoni
edit-paste	editpaste	text edit context menus, kdeprint	final	3		Pinheiro	Vignoni
edit-clear	editclear	text edit context menus	final	3		Vignoni
	messagebox_info	passive popups	approval	1		Pinheiro
	messagebox_warning	passive popups	approval	1		Pinheiro
	messagebox_critical	passive popups, kjs debugger	approval	1		Pinheiro
	history_clear	combobox context menu, html forms	approval	1		Pinheiro
today	today	datepicker	approval	2		Vignoni
arrow-left-double	2leftarrow	datepicker	draft	1
arrow-right-double	2rightarrow	datepicker	draft	1
arrow-left	1leftarrow	datepicker, html	draft	1
arrow-right	1rightarrow	datepicker, html	draft	1
help-contents	contents	help menu, printer config	final	3		Pinheiro	Vignoni
help-whatsthis	contexthelp	help menu	final	3		Vignoni	Pinheiro
about-kde	about_kde	help menu	draft	1		Vignoni
text-completion	completion	line edits context menu	approval	2		Pinheiro
object-rotate-left	rotate_cw	pixmap region selector	final	3		Vignoni
object-rotate-right	rotate_ccw	pixmap region selector	final	3		Vignoni
	spellcheck	text box context menu, kate, spell check action	draft	1		Vignoni
	lock	toolbar context menu, lock overlay	draft	1		Vignoni
	unlock	toolbar context menu	approval	2		Vignoni
	next	next action, kate	approval	2		Vignoni
	previous	previous action, kate	approval	2		Vignoni
	stop	kjs debugger, print preview, print job mgr, khtml/ecma/debugger/images	approval	2		Vignoni
	java	java applets	final	3	see java_kjava	Pinheiro	Vignoni
	1uparrow	khtml	draft	1
	1downarrow	khtml	draft	1
	mail_generic	khtml	final	3		Vignoni
file-broken	file_broken	khtml	final	3	much based on the latest mime sheet david made	Vignoni
	continue	khtml/ecma/debugger/images		Err:508	not using icon theme?!
	step-into	khtml/ecma/debugger/images		Err:508	not using icon theme?!
	step-out	khtml/ecma/debugger/images		Err:508	not using icon theme?!
	step-over	khtml/ecma/debugger/images		Err:508	not using icon theme?!
window-new	window_new	khtml, kate	final	3		Pinheiro	Vignoni
tab-new	tab_new	khtml	final	3		Pinheiro	Vignoni
idea	idea	ktip dialog and action	final	3		Pinheiro	Vignoni
	fileclose	tab bar, javascript error dialog, kross script, actions	final	3		Vignoni
	xapp	window titles	final	3	correct name isn't just “x.svg”?	Pinheiro
	charset	khtml (encodings)		Err:508		Vignoni
print-frame	frameprint	khtml print	final	3		Vignoni
		javascript error dialog, dialog button		Err:508
	images_display	khtml		Err:508
	reload	khtml, kate, print job mgr, printer config	approval	2
document-open	fileopen	url line edit, file dialog, kprinter	final	3		Vignoni
bookmark	bookmark	file dialog, kate, edit bookmark action	final	3		Pinheiro	Vignoni
configure	configure	file dialog, properties dialog, kate	draft	1
	password	password dialog	final	3		Pinheiro	Vignoni
	filesave	download progress, kate, save action	final	3		Pinheiro	Vignoni
	unknown	mimetype dialog	final	3		Vignoni
bookmark-new-list	bookmarks_list_add	bookmark menu	final	3		Pinheiro	Vignoni
bookmark-new	bookmark_add	bookmark menu	final	3		Pinheiro	Vignoni
folder-new	folder_new	bookmark menu, file dialog	final	3		Vignoni
folder	folder	kboomarkmenu, kdeprint	final	3		Vignoni
	thumbnail	image previewer, file dialog	final	3	what if we put a real image in place of the oxy wallpaper?	Vignoni
folder-open	folder_open	url drop list	final	3		Vignoni
	edit	file dialog speedbar, kate	final	3		Pinheiro	Vignoni
	editdelete	file dialog, kdeprint	final	3		Vignoni
	edittrash	file dialog, print job mgr	draft	1	should we just replace this with the trash can from filesystem/? (think so (Pinheiro))	Vignoni
	view_multicolumn	file dialog	final	3		Vignoni
	view_detailed	file dialog	final	3		Vignoni	pinheiro
format-text-bold	text_bold	kate	final	3		Vignoni	pinheiro
format-text-italic	text_italic	kate	final	3		Vignoni	pinheiro
format-text-underline	text_under	kate	final	3		Vignoni	pinheiro
format-text-strikethrough	text_strike	kate	final	3		Vignoni	pinheiro
	view_text	kate	final	3		Vignoni	pinheiro
colorize	colorize	kate	final	3		Pinheiro	Vignoni
	frame_edit	kate	final	3		Vignoni
	rightjust	kate	final	3		Vignoni
	source	kate	final	3		Pinheiro	Vignoni
browser-go	key_enter	kate	final	3		Pinheiro	Vignoni
	connect_established	kate	approval	2		Pinheiro
	indent	kate	final	3		Vignoni
	unindent	kate	final	3		Vignoni
	viewmag	kate	final	3		Pinheiro	Vignoni
	viewmag-	kate	final	3		Vignoni	Pinheiro
	viewmag	actions	final	3		Vignoni	Pinheiro
	sort	kate	approval	Err:508
	filter	kate, kprinter	draft	1		Vignoni
	ok	kate, knewstuff	approval	Err:508
	kdeprint_uploadsmb	cups config (printing)		Err:508
	kdeprint_report	cups config (printing)		Err:508
	filefind	kprinter	draft	1
document-print	fileprint	print preview, print job mgr, print action	final	3		Vignoni
	wizard	kprinter	final	3		Pinheiro
	help	kprinter	approval	2	if it calls the help center why it doesn't use the contents icon that is in “help” menu?	Vignoni
	run	print job mgr		Err:508
	history	print job mgr, knewstuff	draft	1
	personal	print job mgr		Err:508
	kdeprint_printer	print job mgr	final	3	copy of devices/printer	Vignoni
	document	kdeprint		Err:508
	view_change	kdeprint, config shortcuts action		Err:508
	kdeprint_printstate	kdeprint		Err:508		Vignoni
	kdeprint_enableprinter	printer config	approval	Err:508	wrong name in theme or?	Vignoni
	kdeprint_stopprinter	printer config	approval	Err:508	wrong name in theme or?	Vignoni
	kdeprint_queuestate	printer config	approval	Err:508	wrong name in theme or?	Vignoni
	kdeprint_addprinter	printer config	final	3		Vignoni
	kdeprint_addpseudo	printer config	final	3		Vignoni
	kdeprint_defaulthard	printer config		Err:508		Vignoni
	kdeprint_defaultsoft	printer config		Err:508		Vignoni
	kdeprint_testprinter	printer config	final	3		Vignoni
	kdeprint_configmgr	printer config		Err:508		Vignoni
	kdeprint_restartsrv	printer config		Err:508		Vignoni
	kdeprint_configsrv	printer config		Err:508		Vignoni
	kdeprint_printer_infos	printer config	final	3		Vignoni
	network	printer config	final	3		Vignoni
	package_utilities	printer config	final	3		Vignoni
	player_play	kross script, notification dialog	approval	2
	player_stop	kross script	approval	2
	fileimport	kross script	final	3		Vignoni
	knewstuff	kross script, knewstuff	draft	1	looks a lot like bookmarks icon?
document-new	filenew	new action	final	3		Vignoni
	filesaveas	save as action	final	3		Pinheiro	Vignoni
	revert	revert file action	approval	Err:508
document-print-preview	filequickprint	print preview action	final	3		Vignoni
	mail_send	email action	final	3
	exit	quit action	draft	1
	gohome	home action	approval	2
	goto	go to page action	approval	2
	start	first page action	draft	1
	finish	last page action	draft	1
	configure_toolbars	config toolbars action	draft	1
	knotify	config notifications action	approval	2		Pinheiro
dialog-ok	button_ok	dialog button	final	3		Vignoni
dialog-cancel	button_cancel	dialog button	final	3		Vignoni
	apply	dialog button	approval	Err:508	another checkmark! heh. how many do we have? about 8 all exactly the same(and not all in the same place (Pinheiro))	Vignoni
	find	dialog button	draft	1		Pinheiro
	add	dialog button	final	3		Vignoni
	remove	dialog button	final	3		Vignoni